## Test effort est template
Test effort estimation project <<< project name >>>
<<<explaning text>>>
<<<explaning text>>>
| Personal costs | Details |  |  |  | Planning values |  |  | Real values
Id | Task | Number | hours per item | intermediate hours | Comment | Cost / hour | hours | Costs | Cost / hour | hours | Costs
1.1 | <<< task >>> |  |  | 0
1.2 | <<< task >>> |  |  | 0
1.3 | <<< task >>> |  |  | 0
1.4 | <<< task >>> |  |  | 0
1 | Test planning and control |  |  | 0 |  |  | 0 | 0
2.1 | <<< task >>> |  |  | 0
2.2 | <<< task >>> |  |  | 0
2.3 | <<< task >>> |  |  | 0
2.4 | <<< task >>> |  |  | 0
2.5 | <<< task >>> |  |  | 0
2.6 | <<< task >>> |  |  | 0
2.7 | <<< task >>> |  |  | 0
2.8 | <<< task >>> |  |  | 0
2 | Test analysis and design |  |  | 0 |  |  | 0 | 0
3.1 | <<< task >>> |  |  | 0
3.2 | <<< task >>> |  |  | 0
3.3 | <<< task >>> |  |  | 0
3.4 | <<< task >>> |  |  | 0
3.5 | <<< task >>> |  |  | 0
3.6 | <<< task >>> |  |  | 0
3.7 | <<< task >>> |  |  | 0
3.8 | <<< task >>> |  |  | 0
3 | Test implementation and execution |  |  | 0 |  |  | 0 | 0
4 | Evaluating exit criteria and reporting |  |  | 0 |  |  | 0 | 0
5 | Test closure activities |  |  | 0 |  |  | 0 | 0
| Sum | [5 empty] | 0 | 0 |  | 0 | 0
| Material costs |  |  |  |  | Planning values |  |  | Real values
Id | Item |  |  |  |  | Price | Quantity | Costs | Price | Quantity | Costs
M1 | <<< item >>> | [6 empty] | 0
M2 | <<< item >>> | [6 empty] | 0
M3 | <<< item >>> | [6 empty] | 0
0
0
0
0
| Sum | [6 empty] | 0 |  |  | 0
| Overview |  |  |  |  | Planning values |  |  | Real values
| Personal costs | [6 empty] | 0 |  |  | 0
| Material costs | [6 empty] | 0 |  |  | 0
| Intermediate result | [6 empty] | 0
| Risk load | [5 empty] | 20% | 0
| Overall result | [6 empty] | 0 |  |  | 0

## Test effort est example
Test effort estimation project "KU Test Project"
Test project over 8 weeks. 6 iterations planned with weekly deployments on Mondays from 3rd week on
Basic are requirements: User manual of old version, requirements specification, system architecture scetches
| Personal costs | Details |  |  |  | Planning values |  |  | Real values
Id | Task | Number | hours per item | intermediate hours | Comment | Cost / hour | hours | Costs | Cost / hour | hours | Costs
1.1 | Test planning |  |  | 80
1.2 | Test control | 6 | 20 | 120 | 6 weeks 1/2 day
1 | Test planning and control |  |  | 200 |  | 200 | 200 | 40000
2.1 | Training, preparation and execution |  |  | 40
2.2 | Test case preparation | 40 | 5 | 200 | Per test case 5 hours incl. req. review
2.3 | Test data preparation | 40 | 1 | 40 | 1 h effort per test case
2.4 | Test environment preparation |  |  | 80
2.5 | Load and performance test prep. |  |  | 80
2 | Test analysis and design |  |  | 440 |  | 150 | 440 | 66000
3.1 | Test case execution | 80 | 0.5 | 40 | Every test case twice
3.2 | Defect management | 40 | 2 | 80 | 1 defect / test case
3.3 | Operation test environment | 6 | 4 | 24 | 4 hours / week
3.4 | Load and performance tests |  |  | 80
3 | Test implementation and execution |  |  | 224 |  | 150 | 224 | 33600
4 | Evaluating exit criteria and reporting | 6 | 8 | 48 | 8 hours / week | 200 | 48 | 9600
5 | Test closure activities |  |  | 20 | workshop / documentation | 200 | 20 | 4000
| Sum | [5 empty] | 932 | 153200 |  | 0 | 0
| Material costs |  |  |  |  | Planning values |  |  | Real values
Id | Item |  |  |  |  | Price | Quantity | Costs | Price | Quantity | Costs
M1 | Test Mgmt Tool incl. 5 licenses | [6 empty] | 20000
M2 | 3 test laptops |  |  |  |  | 25000 | 3 | 75000
M3 | Load test tool, leasing for 4 weeks |  |  |  |  | 1000 | 4 | 4000
| Sum | [6 empty] | 99000 |  |  | 0
| Overview |  |  |  |  | Planning values |  |  | Real values
| Personal costs | [6 empty] | 153200 |  |  | 0
| Material costs | [6 empty] | 99000 |  |  | 0
| Intermediate result | [6 empty] | 252200
| Risk load | [5 empty] | 20% | 50440
| Overall result | [6 empty] | 302640 |  |  | 0