## BasicData
Basic Data					Explanation
Id	Topic	Value	Entity	Comments
1	Risk Loading		%		in Percentage, effort to be added, e. g. 20 %
2	Number of Use Cases				out of functional specification
3	Number of Business Use Cases				out of business process specification
4	Number of Test Cases				should depend on Use Cases, additional ...
5	Duration of creation of 1 Test Case		hours		including effort for learning, review, rework
6	Duration of execution of 1 Test Case		hours		including documentation, rework
7	Number of Test Cases to be retested				Guess over testing cycle, depends on requested quality and test strategy
8	Number of Test Scenarios				should depend on Business Processes, additional ...
9	Duration of creation of 1 Test Scenario		hours		including effort for learning, review, rework; depends on number of Test Cases per Test Scenario
10	Duration of execution of 1 Test Scenario		hours		including documentation, rework
11	Number of Test Scenarios to be retested				Guess over testing cycle, depends on requested quality and test strategy
12	Number of releases				More releases – earlier defect fix delivery possible, more retesting
13	Number of expected defects per Test Case				Guess concerning Software quality, e. g. 10 Test Case, 9 pass, 1 detects defect – enter 0,1
14	Number of expected defects per Test Scenario				Guess concerning Software quality
15	Duration of administration per defect		hours		Contains notice, assigning, discussion, tracking
					Additional topic #1
					Additional topic #2
					Additional topic #3

			=	Value has to be entered

## BasicTimeData
Basic time data				Explanation
Releases		Date	Contents
Release 2		21.12.2007		“Contents” should describe headlines of delivery, should be found in release notes as well
Release 3		18.01.2008		-- “ -- (like above)
				Optional additional release / version / patch #1
				Optional additional release / version / patch #2
				Optional additional release / version / patch #3
Milestones		Date	Expected results
Milestone 1				“Expected results” should contain headlines of working results of each working group
Milestone 2				-- “ -- (like above)
Milestone 3				-- “ -- (like above)
				Optional additional (intermediate) milestone #1
				Optional additional (intermediate) milestone #2
				Optional additional (intermediate) milestone #3
Test time table	Start date	End date	Comments
Prep				Test Prep(aration) Phase
Exe 02-1 ST				Test Exe(cution) Phase 02-1 (Functional) System Test
Exe 02-2 SIT				Test Exe(cution) Phase 02-2 (Functional) System Integration Test
Exe 02-3 NFR				Test Exe(cution) Phase 02-3 Non-Functional-Requirements Test
Exe 03-1 UAT				Test Exe(cution) Phase 03-1 User Acceptance Test
Compl				Test Compl(ition) Phase – Finalization of Test Phase
				Optional additional test phase #1
				Optional additional test phase #2
				Optional additional test phase #3

## Tasks
Tasks					Explanation
Id	Task	Area	Subject	Estim. / Effort / (hour)	Role	Start date	End date	Area is one of {Prep, Exe with Exe 02-1 ST, Exe 02-2 SIT, Exe 02-3 NFR, Exe 03-1 UAT, Compl} / Subject is result after clustering tasks and collecting fitting title. / Estim(ated) effort (in hours) could either be calculated out of BasicData combined with BasicTimeData or guessed. / Roles should be defined as roles in the test project. / Start date and End date should follow Milestones and / or Test time table out of BasicTimeData
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30