## BasicData
Basic Data |  |  |  |  | Explanation
Id | Topic | Value | Entity | Comments
1 | Risk Loading |  | % |  | in Percentage, effort to be added, e. g. 20 %
2 | Number of Use Cases |  |  |  | out of functional specification
3 | Number of Business Use Cases |  |  |  | out of business process specification
4 | Number of Test Cases |  |  |  | should depend on Use Cases, additional ...
5 | Duration of creation of 1 Test Case |  | hours |  | including effort for learning, review, rework
6 | Duration of execution of 1 Test Case |  | hours |  | including documentation, rework
7 | Number of Test Cases to be retested |  |  |  | Guess over testing cycle, depends on requested quality and test strategy
8 | Number of Test Scenarios |  |  |  | should depend on Business Processes, additional ...
9 | Duration of creation of 1 Test Scenario |  | hours |  | including effort for learning, review, rework; depends on number of Test Cases per Test Scenario
10 | Duration of execution of 1 Test Scenario |  | hours |  | including documentation, rework
11 | Number of Test Scenarios to be retested |  |  |  | Guess over testing cycle, depends on requested quality and test strategy
12 | Number of releases |  |  |  | More releases – earlier defect fix delivery possible, more retesting
13 | Number of expected defects per Test Case |  |  |  | Guess concerning Software quality, e. g. 10 Test Case, 9 pass, 1 detects defect – enter 0,1
14 | Number of expected defects per Test Scenario |  |  |  | Guess concerning Software quality
15 | Duration of administration per defect |  | hours |  | Contains notice, assigning, discussion, tracking
Additional topic #1
Additional topic #2
Additional topic #3
|  |  | = | Value has to be entered

## BasicTimeData
Basic time data |  |  |  | Explanation
Releases |  | Date | Contents
Release 2 |  | 2007-12-21 |  | “Contents” should describe headlines of delivery, should be found in release notes as well
Release 3 |  | 2008-01-18 |  | -- “ -- (like above)
Optional additional release / version / patch #1
Optional additional release / version / patch #2
Optional additional release / version / patch #3
Milestones |  | Date | Expected results
Milestone 1 |  |  |  | “Expected results” should contain headlines of working results of each working group
Milestone 2 |  |  |  | -- “ -- (like above)
Milestone 3 |  |  |  | -- “ -- (like above)
Optional additional (intermediate) milestone #1
Optional additional (intermediate) milestone #2
Optional additional (intermediate) milestone #3
Test time table | Start date | End date | Comments
Prep |  |  |  | Test Prep(aration) Phase
Exe 02-1 ST |  |  |  | Test Exe(cution) Phase 02-1 (Functional) System Test
Exe 02-2 SIT |  |  |  | Test Exe(cution) Phase 02-2 (Functional) System Integration Test
Exe 02-3 NFR |  |  |  | Test Exe(cution) Phase 02-3 Non-Functional-Requirements Test
Exe 03-1 UAT |  |  |  | Test Exe(cution) Phase 03-1 User Acceptance Test
Compl |  |  |  | Test Compl(ition) Phase – Finalization of Test Phase
Optional additional test phase #1
Optional additional test phase #2
Optional additional test phase #3

## Tasks
Tasks | [7 empty] | Explanation
Id | Task | Area | Subject | Estim. Effort (hour) | Role | Start date | End date | Area is one of {Prep, Exe with Exe 02-1 ST, Exe 02-2 SIT, Exe 02-3 NFR, Exe 03-1 UAT, Compl} Subject is result after clustering tasks and collecting fitting title. Estim(ated) effort (in hours) could either be calculated out of BasicData combined with BasicTimeData or guessed. Roles should be defined as roles in the test project. Start date and End date should follow Milestones and / or Test time table out of BasicTimeData
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30