## IncidentTemplate
Attribute | Values
Incident Number |  | = mandatory value
Summary |  | = optional value
Detected
… by author
Last modified
… by author
Assigned to
Product
Detected in version
Target version
Fixed version
Incident Type
Severity
Priority
Status
Description | Description: Steps to Reproduce: Expected Results: Actual Results:
Attachments
Comments
Links
Product values
System1
System2
System3
System4
Other
Incident types
Defect
Change request
Severity
1=Blocker
2=High
3=Medium
4=Low
Priority
1=Very urgent
2=Urgent
3=Medium
4=Low
Status
New
Open
Fixed
Retest
Closed
Rejected
Reopened

## IncidentSample
Attribute | Value (Sample) | Description
Incident Number | 42 | Unique number, typically created by system
Summary | It is not possible to update chosen dates | Headline: Short, one-line statement that summarizes the incident.
Detected | 2012-02-02 06:11 | Date / Time when the incident was created
… by author | Uwe Gühl | Name of person, who created the incident
Last modified | 2012-02-02 06:11 | Date / Time the incident was updated.
… by author | Uwe Gühl | Name of person, who did last modification
Assigned to | John Doe | Name of person, who is currently working on incident, e.g. "Open" -> Developer, "Retest" -> Tester
Product | System2 | Product for which the incident applies. Normally a customized list is offered.
Detected in version | 2.8 | The version, where the incident was detected, should be given here. Version number depends on project, name convention, and development status
Target version | 3.0 | Version, where the incident should be fixed, should be given here.
Fixed version |  | Version, where the incident really got fixed.
Incident Type | Defect | Type of incident, typical values: Defect and change request
Severity | 2=High | This is about, how severe an incident is, possible choices are: 1=Blocker: This is the highest priority and should only be given to incidents associated with crashes, data loss, etc. 2=High: Serious incidents, functionality blocked, only work intensive workaround 3=Medium: Typical defect 4=Low: Not important, like spelling errors
Priority | 2=Urgent | This is about the urgency of fixing, possible choices: 1=Very urgent: Has to be fixed as soon as possible, e.g. with a hot fix 2=Urgent: Has to be fixed for the next regular delivery 3=Medium: Delivery of a fix should be planned 4=Low: To be fix, if time is left Possible special status: 0=No fix: Defect must not be fixed
Status | Open | Current state of the incident, possible choices: New: For all newly created Incidents. Open: An incident where activities are ongoing. Fixed: If an incident has been fixed and is ready for delivery. Retest: Incidents delivered in a release, ready for retest Closed: Final status, no further activities. Rejected: Final status, possible reason: Duplicate, not a defect of software under test. Reopened: If there are still issues with a fixed defect
Description | Description: When opening the invitation link, I access the web site and can see the "guest02" entry, but it is not possible to enter the entry. Steps to Reproduce: - Open invitation email "274948-guest02@spambog.com" - Select invitation 24.02.2012 and click Expected Results: - Entry "guest02" should be editable Actual Results: - No system reaction when clicking on / nearby "guest02" entry | Description of the problem, the steps required to reproduce the problem, the expected results, and the actual results. Description of the solution for the fix by the developer. Information about retest.
Attachments | scheduleonce_guest02_noUpdate.jpg | Everything, that helps to clarify the Incident are attached here, esp. screenshots
Comments |  | For communication of participants, typically logged by the system
Links | TC03 - Update chosen dates Defect41 - Update of wrong guest possible | Links to related test cases, or other related incidents, e. g. duplicates
Product values
System1
System2
System3
System4
Other
Incident types
Defect
Change request
Severity
1=Blocker
2=High
3=Medium
4=Low
Priority
1=Very urgent
2=Urgent
3=Medium
4=Low
Status
New
Open
Fixed
Retest
Closed
Rejected
Reopened